# The Battery Storage Development Handbook: Diligence Checklists

These checklists collect the questions raised in the chapters. They are starting points for a diligence plan, not substitutes for specialist advisers.

## B.1 Site and interconnection

Site

☐ Historical price spread and volatility at the node; capacity zone; planned transmission changes nearby.

☐ Land: acreage, shape, flood zone, access for heavy deliveries, space reserved for augmentation.

☐ Lease: term and extensions, rent and escalation, augmentation rights, decommissioning obligations, assignment and lender protections, estoppel.

☐ Census tract and energy community qualification, documented.

Interconnection

☐ Request in the project company's name and transferable; study stage; deposits and withdrawal penalties.

☐ Assigned upgrades, cost estimate and its firmness; cluster mates and reallocation risk.

☐ Injection and withdrawal limits; charging restrictions; operating conditions.

☐ Deliverability for capacity, or energy only.

☐ Transmission owner's schedule for its work and the consequences of delay.

## B.2 Permits and fire safety

☐ All land use, building, electrical and environmental permits, with their conditions and appeal periods.

☐ Record of consultation with the fire authority; emergency response plan and training of responders.

☐ UL 9540 listing of the exact system; UL 9540A test reports, including large-scale fire testing, at the spacing of the site plan and under the edition the permit requires.

☐ Hazard mitigation analysis, explosion control design, gas detection and ventilation.

☐ Noise, visual and stormwater studies; decommissioning plan and security.

☐ Local history: moratoriums, setback proposals, opposition.

## B.3 Equipment, contracts and trade

☐ Supply agreement: price and adjustments, delivery and delay damages, commissioning tests, certifications, origin documentation.

☐ EPC or balance of plant contract: scope, price, schedule, interfaces, performance guarantees.

☐ Product and performance warranties: term, degradation curve, operating limits (cycles, state of charge, temperature, rates), remedies.

☐ LTSA: scope, availability guarantee and its definition, damages, term and renewal, software and controls coverage.

☐ Augmentation: plan, budget, compatibility, reserved space and inverter capacity, any advance agreement.

☐ Tariffs: equipment list with origins and duties at signing; allocation of tariff changes; customs and forced labor documentation.

☐ Consistency: identical capacity test procedure and availability definition across supply agreement, warranty, LTSA and toll.

## B.4 Revenue

☐ Merchant forecast: source, date, realized or perfect foresight, storage build-out assumed, accreditation path, downside scenario.

☐ Toll or capacity contract: fee, term, guarantees and deductions, dispatch rights, change in law, credit support and its replenishment.

☐ Revenue floor: level, term, sharing, premium, optimization rights, counterparty credit.

☐ Merchant tail: discounted at a merchant rate; haircuts applied to real quantities.

## B.5 Tax credit

☐ Date construction began and evidence (physical work or five percent safe harbor).

☐ Prevailing wage and apprenticeship compliance and records.

☐ Bonuses claimed and their support; eligible basis and exclusions.

☐ Material assistance cost ratio: method (actual costs or safe harbor tables), supplier certifications, result against the threshold for the year construction began.

☐ Ownership: no specified foreign entity or foreign-influenced entity among owners, lenders or licensors; no effective control.

☐ Contracts that could create payments giving effective control within ten years: service, software, augmentation, licensing.

☐ Transfer agreement, buyer, price, indemnities, tax insurance; bridge terms.

☐ Recapture exposure if the project or interests are sold within five years.

## B.6 Financing and model

☐ Term sheet: ratios by revenue type, tenor, reserves (debt service and augmentation), cash sweep, covenants.

☐ Equity return in the lender's downside case.

☐ Model built in AC at the point of interconnection, with realized prices, accredited capacity, augmentation consistent with degradation, cycles within the warranty and discount rates by risk.

☐ Check sheet passing; sensitivities labeled with their financing assumption.

## B.7 Operating asset

☐ Revenue history by layer against forecast and market benchmark.

☐ Annual capacity tests against the warranted curve; augmentation done and remaining.

☐ Availability history by cause; toll deductions; warranty claims.

☐ Remaining warranty and LTSA term and renewal cost.

☐ Thermal incidents, safety findings, insurance claims and premium history.

☐ Cyber security: remote access, rights, standards met.

☐ Credit recapture period and documentation; repowering potential of the site.

Julian R. Sterling, The Battery Storage Development Handbook. Starting points for a diligence plan, not a substitute for specialist advisers.