## Read me
Construction Cost Control -- Workbook 4 of 4
Before Signature: forecast the knowable part of the gap
Julian R. Sterling. Companion files: julianrsterling.com/costcontrol
What this workbook is for
The other three workbooks take one finished project apart. This one is meant to be used on a
project that has not been signed yet. Type your own scheme into the blue cells and it computes
the part of the gap that is knowable at signature, and sets it against the headroom your
appraisal actually has.
It forecasts five lines and refuses to forecast four
It forecasts design development, provisional sums, the post-award pricing premium, prolongation
and the escalation on all four. Those are the lines whose inputs exist before signature.
It does NOT forecast the scope half of client changes, disruption, statutory change or
contra-charges. Those are listed on the Forecast sheet at zero, with a note saying why, because
a forecast that quietly includes an unforecastable line is worse than one that admits the gap.
So the number this workbook produces is a floor, not an estimate of the outturn.
It ships filled in with Pemberton Yard
The blue cells arrive holding the book's own scheme, so the Checks sheet can prove the workbook
reproduces the book before you overtype anything. Overtype the blue cells with your own scheme
and the checks will fail by design: that is the workbook working, not breaking.
No macros, no external links, no protection, no circular references.

## Your project
Your project
Overtype the blue cells. Everything else in this file is a formula.
The scheme
Units | 96
Gross internal area, m2 | 8640
Net internal area, m2 | 7344
Contract period, weeks | 94
The tender, as priced
Measured works rate, per m2 | 2180 | From the priced document, not the summary
External works and site | 1240000
Preliminaries, per cent of works | 15%
Overheads and profit, per cent of works plus prelims | 6%
Contractor's design development allowance, per cent | 2% | The first loss layer. Ask for it as a figure, not a summary line
Provisional sums | 1340000 | Count them. List them. Say which are undesignable
What you can measure today
Design information issued at contract | 72% | Counted package by package. This is the input everything runs on
Premium on value priced after award | 13.5% | Ask your cost consultant to defend this figure in writing
Time-related share of preliminaries | 72%
Months from tender to the midpoint of work that will be priced later | 19
Escalation index a year | 4.1%
What you have to assume, and should assume out loud
Provisional sums: the amount you expect them to release at | 2150000 | Re-estimate each sum against a real specification. The book's project released at 1.604 times its allowance.
Client changes you expect to instruct, at contract rates | 742000 | Bought, not lost. Say so in the board paper
Post-award pricing premium you expect to pay on them | 14.2%
Weeks of extension of time you expect to grant | 11
Implied overrun on the provisional sums | 60.45%
Your appraisal
Revenue per unit | 472000
Land | 6200000
Professional fees, per cent of construction cost | 9.8%
Sale costs, per cent of revenue | 2.2%
Loan to cost | 65%
Average drawn share | 60%
Interest rate a year | 7.9%
Term, years | 2.4
Target profit on cost | 15% | Headroom does not exist without a stated threshold
Retention time value credited against finance | 71923

## Contract sum
Your contract sum, rebuilt layer by layer
Each layer sits on the layer beneath it
Measured works | 18835200
External works and site | 1240000
Works total | 20075200
Preliminaries | 3011280 | Of the works
Overheads and profit | 1385188.8 | Of works PLUS preliminaries
Subtotal before the allowance | 24471668.8 | This is also the value exposed to late design
Contractor's design development allowance | 489433.376
Provisional sums | 1340000
CONTRACT SUM | 26301102.176
Cost per m2 of gross internal area | 3044.109
Cost per unit | 273969.8143
Time-related preliminaries per week | 23065.1234 | The single most useful figure nobody quotes
Value that will be priced after signature | 6852067.264 | An arithmetical statement, not a forecast

## Forecast
What the knowable lines say, before you sign
Line | Amount | Kind | How it is computed, and why it is knowable
Forecast: the five lines whose inputs exist today
Design development beyond the allowance | 435595.7046 | lost | Value priced late, times the premium, less the contractor's first loss layer. All four inputs are on the priced document or are a count.
Provisional sums released above allowance | 810000 | lost | Your allowance times your assumed release multiple. The allowance is a fact; the multiple is an assumption you are making out loud.
Client changes, premium for pricing after award | 105364 | lost | The premium is a property of the contract, not of the change. It is knowable even though the changes are not.
Prolongation of time-related preliminaries | 253716.3574 | lost | The weekly rate is derivable from the tender today. Only the number of weeks is a judgement.
Escalation on the work priced after the tender | 137483.6016 | lost | A tax on the lines above. The index is a market fact; the lag is a project fact you control.
FORECAST OF THE KNOWABLE GAP | 1742159.6637
As a share of the contract sum | 6.624%
Declared, and deliberately not forecast
Client changes, the scope itself | 742000 | bought | Building you will actually receive. Shown here because it will appear in the account, but it is not a loss and it is not knowable.
Disruption, lost labor productivity | 0 | lost | The one large line whose inputs do not exist before signature. Left at zero. Instrument the records instead of forecasting it.
Statutory change after contract | 0 | bought | Foreseeable in kind, not quantifiable in amount. This is what a contingency is actually for.
Credits: contra-charges, damages, retention | 0 | recovered | Left at zero on purpose. A forecast that books its credits in advance is not prudent.
Contract sum | 26301102.176
Plus the forecast knowable gap | 1742159.6637
Plus the scope you expect to buy | 742000
FLOOR ON THE FINAL ACCOUNT | 28785261.8397
This is a floor, not an estimate. Four lines above it are declared at zero.

## Headroom
Set the forecast against what your appraisal can absorb
Your appraisal at the contract sum
Revenue | 45312000
Construction | 26301102.176
Fees | 2577508.0132
Finance, net of the retention credit | 2521929.7518
Land | 6200000
Sale costs | 996864
Total cost | 38597403.9411
Profit | 6714596.0589
Profit on cost | 17.4%
Meets the target | yes
Headroom
Break-even construction cost | 27033647.8858 | Closed form. Fees move with construction cost and the facility is held at its sized amount, so no iteration is needed.
HEADROOM above the contract sum | 732545.7098
Headroom as a share of the contract sum | 2.785%
The verdict
Forecast of the knowable gap | 1742159.6637
Headroom | 732545.7098
Knowable gap as a multiple of the headroom | 2.3782
Reading | The part of the gap you can already measure exceeds every pound of overrun this appraisal can absorb. The scheme is committed to missing its target before the contract is signed.
Floor on the final account | 28785261.8397
Break-even construction cost | 27033647.8858
Floor less break-even | 1751613.9539 | A positive figure here means the scheme misses its target on the floor alone, before disruption, statutory change or the scope premium.

## Checks
Checks
This workbook ships filled in with the book's own scheme, so it can prove itself before you use it.
Once you overtype the blue cells with your own project, these checks will fail. That is the workbook working, not breaking.
Figure | As printed in the book | Computed | Difference | Verdict | Tolerance
Your contract sum
Contract sum | 26301102 | 26301102 | 0 | PASS | 1
Works total | 20075200 | 20075200 | 0 | PASS | 1
Preliminaries | 3011280 | 3011280 | 0 | PASS | 1
Overheads and profit | 1385189 | 1385189 | 0 | PASS | 1
Value exposed to late design | 24471669 | 24471669 | 0 | PASS | 1
Design development allowance | 489433 | 489433 | 0 | PASS | 1
Cost per m2 | 3044 | 3044 | 0 | PASS | 1
Cost per unit | 273970 | 273970 | 0 | PASS | 1
Time-related preliminaries per week | 23065 | 23065 | 0 | PASS | 1
Value priced after signature | 6852067 | 6852067 | 0 | PASS | 1
The forecast of the knowable gap
Design development beyond the allowance | 435596 | 435596 | 0 | PASS | 1
Provisional sums released above allowance | 810000 | 810000 | 0 | PASS | 1
Client changes, premium | 105364 | 105364 | 0 | PASS | 1
Prolongation | 253716 | 253716 | 0 | PASS | 1
Escalation | 137484 | 137484 | 0 | PASS | 1
FORECAST OF THE KNOWABLE GAP | 1742160 | 1742160 | 0 | PASS | 1
Implied provisional sum overrun | 60.4% | 60.4% | 0 | PASS | 1e-08
Your appraisal and your headroom
Fees at the contract sum | 2577508 | 2577508 | 0 | PASS | 1
Finance, net of the retention credit | 2521929 | 2521930 | 1 | PASS | 1
Sale costs | 996864 | 996864 | 0 | PASS | 1
Total cost | 38597404 | 38597404 | 0 | PASS | 1
Profit | 6714596 | 6714596 | 0 | PASS | 1
Profit on cost | 17.4% | 17.4% | 0 | PASS | 1e-08
Break-even construction cost | 27033648 | 27033648 | 0 | PASS | 1
HEADROOM | 732546 | 732546 | 0 | PASS | 1
Headroom as a share of the contract sum | 2.8% | 2.8% | 0 | PASS | 1e-08
Checks run | 26
PASS | 26
FAIL | 0
Note: money is checked to the pound, because the retention time value is carried in rounded from Workbook 1.