## Read me
Construction Cost Control -- Workbook 3 of 4
Sensitivities: which input actually moves the answer
Julian R. Sterling. Companion files: julianrsterling.com/costcontrol
What this workbook does
Six one-input sensitivities on the Case A bridge, plus design completeness read against the
developer's return. Chapter 14 prints only the movement column. This workbook prints all
eleven lines for every scenario, so you can see which lines moved and which did not.
The rule these tables obey
Every table holds the contract sum where it is. A table that re-priced the contract sum as the
input moved would not be a stress test, it would be a re-pricing, and the gap would never
widen. The re-priced case is Case B, and it lives in Workbook 1 as a separate scenario.
The tables are one input at a time, and the real inputs are correlated
A project that signs at 55 per cent design completion also has more provisional sums, a longer
lag to the midpoint of late-priced work, more causative events and more weeks of extension of
time. Every one of these inputs moves together in practice, so these tables understate the range.
Blue text is an input. The shaded row in each table is the base case. Black text is a formula.
No macros, no external links, no protection, no circular references.
Revised 24 September 2026
The column headings of the six tables sat one column to the left of their figures (MOVEMENT over the retention, Gap over the movement); they are realigned.
The Ranking sheet now sorts the six inputs by span, as the book describes it, and its control column follows the table printed in Chapter 14.

## Inputs
Case A inputs
Identical to Workbook 1, Case A. Change one here and every table below moves with it.
The scheme
Units | 96
Gross internal area, m2 | 8640
Net internal area, m2 | 7344
Contract period, weeks | 94
Contract sum build-up
Measured works rate, per m2 | 2180
External works and site | 1240000
Preliminaries, per cent of works | 15%
Overheads and profit, per cent | 6%
Design development allowance, per cent | 2%
Provisional sums | 1340000
Bridge inputs
Design information issued at contract | 72%
Premium on value priced after award | 13.5%
Provisional sums released | 2150000
Client changes at contract rates | 742000
Post-award pricing premium | 14.2%
Weeks late | 14
Weeks carrying an extension of time | 11
Time-related share of preliminaries | 72%
Trade value exposed to disruption | 11200000
Disrupted weeks | 22
Labor productivity loss | 11%
Statutory change, cost | 310000
Escalation index, per year | 4.1%
Months tender to midpoint of late work | 19
Contra-charges | 96000
Liquidated damages per week | 14500
Liquidated damages cap, per cent | 5%
Retention, per cent | 3%
Retention never released, per cent | 11.5%
Appraisal inputs (for the seventh table)
Revenue per unit | 472000
Land | 6200000
Professional fees, per cent of construction cost | 9.8%
Sale costs, per cent of revenue | 2.2%
Loan to cost | 65%
Average drawn share | 60%
Interest rate a year | 7.9%
Term, years | 2.4
Target profit on cost | 15%
Retention time value credited against finance | 71923

## Base
The contract sum, computed once and held
No sensitivity below moves any of these. That is the point of Chapter 14.
Contract sum
Measured works | 18835200
External works and site | 1240000
Works total | 20075200
Preliminaries | 3011280
Overheads and profit | 1385188.8
Subtotal before the allowance | 24471668.8 | Also the value exposed to late design
Design development allowance | 489433.376
Provisional sums | 1340000
CONTRACT SUM | 26301102.176
Constants used by every table
Time-related preliminaries per week | 23065.1234
Trade spend per week | 119148.9362
Liquidated damages cap | 1315055.1088
Retention held | 789033.0653
Revenue | 45312000
Finance at the sized facility, net of the retention credit | 2521929.7518
Sale costs | 996864

## Sensitivities
Six one-input sensitivities on the Case A bridge
Each table moves ONE input and holds the contract sum where it is. The shaded row is the base case.
Design information issued at contract
Steep at the bottom, then a plateau: past about 85 per cent the contractor's allowance absorbs the whole of the remaining exposure and none of it reaches the client.
Input | Design development | Provisional sums | Client changes, scope | Client changes, premium | Prolongation | Disruption | Statutory change | Escalation | Contra-charges | Liquidated damages | Retention never released | MOVEMENT | Gap | Final account
55% | 997220.5036 | 810000 | 742000 | 105364 | 253716.3574 | 288340.4255 | 310000 | 174375.9507 | -96000 | -43500 | -90738.8025 | 3450778.4348 | 13.12% | 29751880.6108
65% | 666852.9748 | 810000 | 742000 | 105364 | 253716.3574 | 288340.4255 | 310000 | 152674.5689 | -96000 | -43500 | -90738.8025 | 3098709.5242 | 11.78% | 29399811.7002
72% | 435595.7046 | 810000 | 742000 | 105364 | 253716.3574 | 288340.4255 | 310000 | 137483.6016 | -96000 | -43500 | -90738.8025 | 2852261.2867 | 10.84% | 29153363.4627
85% | 6117.9172 | 810000 | 742000 | 105364 | 253716.3574 | 288340.4255 | 310000 | 109271.8052 | -96000 | -43500 | -90738.8025 | 2394571.7029 | 9.104% | 28695673.8789
96% | 0 | 810000 | 742000 | 105364 | 253716.3574 | 288340.4255 | 310000 | 108869.9278 | -96000 | -43500 | -90738.8025 | 2388051.9083 | 9.08% | 28689154.0843
Span (highest movement less lowest) | [11 empty] | 1062726.5265
Provisional sums released
Close to linear: every pound above the allowance is a pound of gap, plus the escalation on it. The first row is the case where the sums release exactly at allowance.
Input | Design development | Provisional sums | Client changes, scope | Client changes, premium | Prolongation | Disruption | Statutory change | Escalation | Contra-charges | Liquidated damages | Retention never released | MOVEMENT | Gap | Final account
1340000 | 435595.7046 | 0 | 742000 | 105364 | 253716.3574 | 288340.4255 | 310000 | 84275.8322 | -96000 | -43500 | -90738.8025 | 1989053.5173 | 7.563% | 28290155.6933
1600000 | 435595.7046 | 260000 | 742000 | 105364 | 253716.3574 | 288340.4255 | 310000 | 101354.8693 | -96000 | -43500 | -90738.8025 | 2266132.5544 | 8.616% | 28567234.7304
1900000 | 435595.7046 | 560000 | 742000 | 105364 | 253716.3574 | 288340.4255 | 310000 | 121061.4506 | -96000 | -43500 | -90738.8025 | 2585839.1357 | 9.832% | 28886941.3117
2150000 | 435595.7046 | 810000 | 742000 | 105364 | 253716.3574 | 288340.4255 | 310000 | 137483.6016 | -96000 | -43500 | -90738.8025 | 2852261.2867 | 10.84% | 29153363.4627
2600000 | 435595.7046 | 1260000 | 742000 | 105364 | 253716.3574 | 288340.4255 | 310000 | 167043.4735 | -96000 | -43500 | -90738.8025 | 3331821.1586 | 12.67% | 29632923.3346
Span (highest movement less lowest) | [11 empty] | 1342767.6413
Post-award pricing premium on client changes
The flattest table in the book, and the line clients spend the most management attention on.
Input | Design development | Provisional sums | Client changes, scope | Client changes, premium | Prolongation | Disruption | Statutory change | Escalation | Contra-charges | Liquidated damages | Retention never released | MOVEMENT | Gap | Final account
0% | 435595.7046 | 810000 | 742000 | 0 | 253716.3574 | 288340.4255 | 310000 | 130562.3875 | -96000 | -43500 | -90738.8025 | 2739976.0726 | 10.42% | 29041078.2486
6.1% | 435595.7046 | 810000 | 742000 | 45262 | 253716.3574 | 288340.4255 | 310000 | 133535.5851 | -96000 | -43500 | -90738.8025 | 2788211.2702 | 10.6% | 29089313.4462
10% | 435595.7046 | 810000 | 742000 | 74200 | 253716.3574 | 288340.4255 | 310000 | 135436.4819 | -96000 | -43500 | -90738.8025 | 2819050.1671 | 10.72% | 29120152.3431
14.2% | 435595.7046 | 810000 | 742000 | 105364 | 253716.3574 | 288340.4255 | 310000 | 137483.6016 | -96000 | -43500 | -90738.8025 | 2852261.2867 | 10.84% | 29153363.4627
22% | 435595.7046 | 810000 | 742000 | 163240 | 253716.3574 | 288340.4255 | 310000 | 141285.3953 | -96000 | -43500 | -90738.8025 | 2913939.0804 | 11.08% | 29215041.2564
Span (highest movement less lowest) | [11 empty] | 173963.0077
Weeks of extension of time granted
Not linear as it first appears: each week of extension also removes a week of liquidated damages, and past 14 there are no contractor-risk weeks left to convert.
Input | Design development | Provisional sums | Client changes, scope | Client changes, premium | Prolongation | Disruption | Statutory change | Escalation | Contra-charges | Liquidated damages | Retention never released | MOVEMENT | Gap | Final account
0 | 435595.7046 | 810000 | 742000 | 105364 | 0 | 288340.4255 | 310000 | 137483.6016 | -96000 | -203000 | -90738.8025 | 2439044.9293 | 9.274% | 28740147.1053
4 | 435595.7046 | 810000 | 742000 | 105364 | 92260.4936 | 288340.4255 | 310000 | 137483.6016 | -96000 | -145000 | -90738.8025 | 2589305.4229 | 9.845% | 28890407.5989
8 | 435595.7046 | 810000 | 742000 | 105364 | 184520.9872 | 288340.4255 | 310000 | 137483.6016 | -96000 | -87000 | -90738.8025 | 2739565.9165 | 10.42% | 29040668.0925
11 | 435595.7046 | 810000 | 742000 | 105364 | 253716.3574 | 288340.4255 | 310000 | 137483.6016 | -96000 | -43500 | -90738.8025 | 2852261.2867 | 10.84% | 29153363.4627
16 | 435595.7046 | 810000 | 742000 | 105364 | 369041.9745 | 288340.4255 | 310000 | 137483.6016 | -96000 | 0 | -90738.8025 | 3011086.9037 | 11.45% | 29312189.0797
Span (highest movement less lowest) | [11 empty] | 572041.9745
Labor productivity loss
Even at zero this project still moves by most of its gap. Disruption is not the story here.
Input | Design development | Provisional sums | Client changes, scope | Client changes, premium | Prolongation | Disruption | Statutory change | Escalation | Contra-charges | Liquidated damages | Retention never released | MOVEMENT | Gap | Final account
0% | 435595.7046 | 810000 | 742000 | 105364 | 253716.3574 | 0 | 310000 | 137483.6016 | -96000 | -43500 | -90738.8025 | 2563920.8612 | 9.748% | 28865023.0372
5% | 435595.7046 | 810000 | 742000 | 105364 | 253716.3574 | 131063.8298 | 310000 | 137483.6016 | -96000 | -43500 | -90738.8025 | 2694984.691 | 10.25% | 28996086.867
8% | 435595.7046 | 810000 | 742000 | 105364 | 253716.3574 | 209702.1277 | 310000 | 137483.6016 | -96000 | -43500 | -90738.8025 | 2773622.9888 | 10.55% | 29074725.1648
11% | 435595.7046 | 810000 | 742000 | 105364 | 253716.3574 | 288340.4255 | 310000 | 137483.6016 | -96000 | -43500 | -90738.8025 | 2852261.2867 | 10.84% | 29153363.4627
16% | 435595.7046 | 810000 | 742000 | 105364 | 253716.3574 | 419404.2553 | 310000 | 137483.6016 | -96000 | -43500 | -90738.8025 | 2983325.1165 | 11.34% | 29284427.2925
Span (highest movement less lowest) | [11 empty] | 419404.2553
Escalation index a year
A derived line: escalation is a tax on the other lines, computed on a base the other inputs set.
Input | Design development | Provisional sums | Client changes, scope | Client changes, premium | Prolongation | Disruption | Statutory change | Escalation | Contra-charges | Liquidated damages | Retention never released | MOVEMENT | Gap | Final account
0% | 435595.7046 | 810000 | 742000 | 105364 | 253716.3574 | 288340.4255 | 310000 | 0 | -96000 | -43500 | -90738.8025 | 2714777.6851 | 10.32% | 29015879.8611
2% | 435595.7046 | 810000 | 742000 | 105364 | 253716.3574 | 288340.4255 | 310000 | 66662.6071 | -96000 | -43500 | -90738.8025 | 2781440.2922 | 10.58% | 29082542.4682
4.1% | 435595.7046 | 810000 | 742000 | 105364 | 253716.3574 | 288340.4255 | 310000 | 137483.6016 | -96000 | -43500 | -90738.8025 | 2852261.2867 | 10.84% | 29153363.4627
7% | 435595.7046 | 810000 | 742000 | 105364 | 253716.3574 | 288340.4255 | 310000 | 236660.8081 | -96000 | -43500 | -90738.8025 | 2951438.4932 | 11.22% | 29252540.6692
10% | 435595.7046 | 810000 | 742000 | 105364 | 253716.3574 | 288340.4255 | 310000 | 340920.9859 | -96000 | -43500 | -90738.8025 | 3055698.6711 | 11.62% | 29356800.8471
Span (highest movement less lowest) | [11 empty] | 340920.9859

## Ranking
The six inputs, ranked by span
Span is the difference between the largest and smallest movement the table produces.
Input, largest span first | Span | Share of the base gap | Does the client control it before signature? | Working: the six tables in chapter order | Span | Client control before signature (Chapter 14)
Provisional sums released | 1342767.6413 | 47.08% | Full. The schedule of sums is written by the client's team before tender. | Design information issued at contract | 1062726.5265 | Full. It is a measurement of the client's own design program.
Design information issued at contract | 1062726.5265 | 37.26% | Full. It is a measurement of the client's own design program. | Provisional sums released | 1342767.6413 | Full. The schedule of sums is written by the client's team before tender.
Weeks of extension of time granted | 572041.9745 | 20.06% | None directly. The client's influence is exercised before signature, through the events its documents generate and the records its contract requires. | Post-award pricing premium on client changes | 173963.0077 | Partial. The premium follows leverage, and leverage follows completeness.
Labor productivity loss | 419404.2553 | 14.7% | Minimal. Not knowable at signature (Chapter 7). | Weeks of extension of time granted | 572041.9745 | None directly. The client's influence is exercised before signature, through the events its documents generate and the records its contract requires.
Escalation index a year | 340920.9859 | 11.95% | None. The index is a market fact, though the base exposed to it is not. | Labor productivity loss | 419404.2553 | Minimal. Not knowable at signature (Chapter 7).
Post-award pricing premium on client changes | 173963.0077 | 6.099% | Partial. The premium follows leverage, and leverage follows completeness. | Escalation index a year | 340920.9859 | None. The index is a market fact, though the base exposed to it is not.
Largest single-input span | 1342767.6413
The joint move (Case B, Workbook 1): final account lower by | 1620289
The joint move exceeds the largest single move by | 277521.3587
Read this ranking as a ranking of THIS project's inputs at THIS project's values.
What generalizes is the method and the two rules on the Read me sheet, not the order.
Revised 24 September 2026: the rows are now sorted by span (they were in chapter order), and the control column follows the table in Chapter 14.

## Design vs Profit
Design completeness read against the developer's return
The contract sum is held where it is, so this is a stress test and not a procurement. Case B is a different contract sum.
Design issued at contract | Movement | Gap | Final account | Fees | Total cost | Profit | Profit on cost | Clears the target
55% | 3450778.4348 | 13.12% | 29751880.6108 | 2915684.2999 | 42386358.6625 | 2925641.3375 | 6.902% | no | 997220.5036 | 174375.9507
65% | 3098709.5242 | 11.78% | 29399811.7002 | 2881181.5466 | 41999786.9986 | 3312213.0014 | 7.886% | no | 666852.9748 | 152674.5689
72% | 2852261.2867 | 10.84% | 29153363.4627 | 2857029.6193 | 41729186.8339 | 3582813.1661 | 8.586% | no | 435595.7046 | 137483.6016
80% | 2570606.1582 | 9.774% | 28871708.3342 | 2829427.4168 | 41419929.5028 | 3892070.4972 | 9.397% | no | 171301.6816 | 120122.4961
85% | 2394571.7029 | 9.104% | 28695673.8789 | 2812176.0401 | 41226643.6709 | 4085356.3291 | 9.91% | no | 6117.9172 | 109271.8052
90% | 2388051.9083 | 9.08% | 28689154.0843 | 2811537.1003 | 41219484.9363 | 4092515.0637 | 9.929% | no | 0 | 108869.9278
96% | 2388051.9083 | 9.08% | 28689154.0843 | 2811537.1003 | 41219484.9363 | 4092515.0637 | 9.929% | no | 0 | 108869.9278
Not one row clears the target.
Design completeness alone, without re-pricing the contract, cannot rescue a scheme whose headroom is 2.8 per cent.
Columns K and L are working columns for the design development line and the escalation on it.

## Checks
Checks
Every figure as printed in the book, beside the figure this workbook computes.
A FAIL means the workbook is wrong, not the book. Everything here is computed from the raw inputs, so every check is exact.
Figure | As printed | Computed | Difference | Verdict | Tolerance
The contract sum, held by every table
Contract sum | 26301102 | 26301102 | 0 | PASS | 1e-08
Value exposed to late design | 24471669 | 24471669 | 0 | PASS | 1e-08
Design information issued at contract
Movement, row 1 | 3450778 | 3450778 | 0 | PASS | 1e-08
Final account, row 1 | 29751881 | 29751881 | 0 | PASS | 1e-08
Movement, row 2 | 3098710 | 3098710 | 0 | PASS | 1e-08
Final account, row 2 | 29399812 | 29399812 | 0 | PASS | 1e-08
Movement, row 3 | 2852261 | 2852261 | 0 | PASS | 1e-08
Final account, row 3 | 29153363 | 29153363 | 0 | PASS | 1e-08
Movement, row 4 | 2394572 | 2394572 | 0 | PASS | 1e-08
Final account, row 4 | 28695674 | 28695674 | 0 | PASS | 1e-08
Movement, row 5 | 2388052 | 2388052 | 0 | PASS | 1e-08
Final account, row 5 | 28689154 | 28689154 | 0 | PASS | 1e-08
Provisional sums released
Movement, row 1 | 1989054 | 1989054 | 0 | PASS | 1e-08
Final account, row 1 | 28290156 | 28290156 | 0 | PASS | 1e-08
Movement, row 2 | 2266133 | 2266133 | 0 | PASS | 1e-08
Final account, row 2 | 28567235 | 28567235 | 0 | PASS | 1e-08
Movement, row 3 | 2585839 | 2585839 | 0 | PASS | 1e-08
Final account, row 3 | 28886941 | 28886941 | 0 | PASS | 1e-08
Movement, row 4 | 2852261 | 2852261 | 0 | PASS | 1e-08
Final account, row 4 | 29153363 | 29153363 | 0 | PASS | 1e-08
Movement, row 5 | 3331821 | 3331821 | 0 | PASS | 1e-08
Final account, row 5 | 29632923 | 29632923 | 0 | PASS | 1e-08
Post-award pricing premium
Movement, row 1 | 2739976 | 2739976 | 0 | PASS | 1e-08
Final account, row 1 | 29041078 | 29041078 | 0 | PASS | 1e-08
Movement, row 2 | 2788211 | 2788211 | 0 | PASS | 1e-08
Final account, row 2 | 29089313 | 29089313 | 0 | PASS | 1e-08
Movement, row 3 | 2819050 | 2819050 | 0 | PASS | 1e-08
Final account, row 3 | 29120152 | 29120152 | 0 | PASS | 1e-08
Movement, row 4 | 2852261 | 2852261 | 0 | PASS | 1e-08
Final account, row 4 | 29153363 | 29153363 | 0 | PASS | 1e-08
Movement, row 5 | 2913939 | 2913939 | 0 | PASS | 1e-08
Final account, row 5 | 29215041 | 29215041 | 0 | PASS | 1e-08
Weeks of extension of time
Movement, row 1 | 2439045 | 2439045 | 0 | PASS | 1e-08
Final account, row 1 | 28740147 | 28740147 | 0 | PASS | 1e-08
Movement, row 2 | 2589305 | 2589305 | 0 | PASS | 1e-08
Final account, row 2 | 28890408 | 28890408 | 0 | PASS | 1e-08
Movement, row 3 | 2739566 | 2739566 | 0 | PASS | 1e-08
Final account, row 3 | 29040668 | 29040668 | 0 | PASS | 1e-08
Movement, row 4 | 2852261 | 2852261 | 0 | PASS | 1e-08
Final account, row 4 | 29153363 | 29153363 | 0 | PASS | 1e-08
Movement, row 5 | 3011087 | 3011087 | 0 | PASS | 1e-08
Final account, row 5 | 29312189 | 29312189 | 0 | PASS | 1e-08
Labor productivity loss
Movement, row 1 | 2563921 | 2563921 | 0 | PASS | 1e-08
Final account, row 1 | 28865023 | 28865023 | 0 | PASS | 1e-08
Movement, row 2 | 2694985 | 2694985 | 0 | PASS | 1e-08
Final account, row 2 | 28996087 | 28996087 | 0 | PASS | 1e-08
Movement, row 3 | 2773623 | 2773623 | 0 | PASS | 1e-08
Final account, row 3 | 29074725 | 29074725 | 0 | PASS | 1e-08
Movement, row 4 | 2852261 | 2852261 | 0 | PASS | 1e-08
Final account, row 4 | 29153363 | 29153363 | 0 | PASS | 1e-08
Movement, row 5 | 2983325 | 2983325 | 0 | PASS | 1e-08
Final account, row 5 | 29284427 | 29284427 | 0 | PASS | 1e-08
Escalation index
Movement, row 1 | 2714778 | 2714778 | 0 | PASS | 1e-08
Final account, row 1 | 29015880 | 29015880 | 0 | PASS | 1e-08
Movement, row 2 | 2781440 | 2781440 | 0 | PASS | 1e-08
Final account, row 2 | 29082542 | 29082542 | 0 | PASS | 1e-08
Movement, row 3 | 2852261 | 2852261 | 0 | PASS | 1e-08
Final account, row 3 | 29153363 | 29153363 | 0 | PASS | 1e-08
Movement, row 4 | 2951438 | 2951438 | 0 | PASS | 1e-08
Final account, row 4 | 29252541 | 29252541 | 0 | PASS | 1e-08
Movement, row 5 | 3055699 | 3055699 | 0 | PASS | 1e-08
Final account, row 5 | 29356801 | 29356801 | 0 | PASS | 1e-08
Design completeness against profit
Movement at 55 per cent | 3450778 | 3450778 | 0 | PASS | 1e-08
Final account at 55 per cent | 29751881 | 29751881 | 0 | PASS | 1e-08
Profit on cost at 55 per cent | 6.9% | 6.9% | 0 | PASS | 1e-08
Movement at 65 per cent | 3098710 | 3098710 | 0 | PASS | 1e-08
Final account at 65 per cent | 29399812 | 29399812 | 0 | PASS | 1e-08
Profit on cost at 65 per cent | 7.89% | 7.89% | 0 | PASS | 1e-08
Movement at 72 per cent | 2852261 | 2852261 | 0 | PASS | 1e-08
Final account at 72 per cent | 29153363 | 29153363 | 0 | PASS | 1e-08
Profit on cost at 72 per cent | 8.59% | 8.59% | 0 | PASS | 1e-08
Movement at 80 per cent | 2570606 | 2570606 | 0 | PASS | 1e-08
Final account at 80 per cent | 28871708 | 28871708 | 0 | PASS | 1e-08
Profit on cost at 80 per cent | 9.4% | 9.4% | 0 | PASS | 1e-08
Movement at 85 per cent | 2394572 | 2394572 | 0 | PASS | 1e-08
Final account at 85 per cent | 28695674 | 28695674 | 0 | PASS | 1e-08
Profit on cost at 85 per cent | 9.91% | 9.91% | 0 | PASS | 1e-08
Movement at 90 per cent | 2388052 | 2388052 | 0 | PASS | 1e-08
Final account at 90 per cent | 28689154 | 28689154 | 0 | PASS | 1e-08
Profit on cost at 90 per cent | 9.93% | 9.93% | 0 | PASS | 1e-08
Movement at 96 per cent | 2388052 | 2388052 | 0 | PASS | 1e-08
Final account at 96 per cent | 28689154 | 28689154 | 0 | PASS | 1e-08
Profit on cost at 96 per cent | 9.93% | 9.93% | 0 | PASS | 1e-08
Ranking and layout (revised 24 September 2026)
Ranking: spans in descending order (1 = yes) | 1 | 1 | 0 | PASS | 1e-08
Ranking: first is provisional sums, second design completeness (1 = yes) | 1 | 1 | 0 | PASS | 1e-08
Ranking: last is the post-award pricing premium (1 = yes) | 1 | 1 | 0 | PASS | 1e-08
Tables: the MOVEMENT header sits over the column that sums the eleven lines (1 = yes, all six tables) | 1 | 1 | 0 | PASS | 1e-08
Checks run | 87
PASS | 87
FAIL | 0